## Agenda Fathir
Agenda Detail — Fathir (1.1 Komunikasi MAVLink · 1.2 Kalibrasi Kamera · 4.1 Uji Simulasi & Deteksi ArUco)
Starts 6 Oct 2026. Blue = my work week · Black = no-work week (from Timelinev2) · Grey = teammate's slot I depend on · Orange = meeting / report milestone. Original WBS in bold; sub-items x.y.z are the new detailed breakdown.
WBS | Kegiatan / Task | Deliverable / Kriteria selesai | Butuh input dari | PJ | Okt |  |  |  | Nov |  |  |  | Des |  |  |  | Jan |  |  |  | Status
[5 empty] | W1 6–7 Okt | W2 8–14 Okt | W3 15–21 Okt | W4 22–31 Okt | W1 1–7 Nov | W2 8–14 Nov | W3 15–21 Nov | W4 22–30 Nov | W1 1–7 Des | W2 8–14 Des | W3 15–21 Des | W4 22–31 Des | W1 1–7 Jan | W2 8–14 Jan | W3 15–21 Jan | W4 22–31 Jan
0 | Milestone tim (konteks)
0.0 | Konsultasi dosen pembimbing + persiapan presentasi | Bring: progress demo / plots from my items |  | Aga
0.1 | Konsultasi & bertemu klien | Bring: detection demo (Okt), SITL loop (Des), field results (Jan) |  | Aga
0.2 | Laporan kemajuan | My sections must be sent to Aga BEFORE Okt W2 (see 1.1.0) |  | Aga
1 | Arsitektur & Perancangan Awal
1.1 | Perancangan komunikasi MAVLink (pymavlink) — was 'Dronekit' | Companion ↔ FC link proven on real drone; mode logic agreed |  | Fathir
1.1.0 | Write progress-report section: comms + calibration status, honest list of what is SITL-only | ½–1 page + figures sent to Aga | Aga: report template & deadline | Fathir | [16 empty] | Not started
1.1.1 | Rework MAVLink layer in SITL: single reader thread caching latest msg per type + timestamps; stale-data = invalid (no zero fallback) | mavlink_iface.py passes SITL run; no dropped ATTITUDE/LOCAL_POSITION_NED |  | Fathir | [16 empty] | Not started
1.1.2 | Decide landing trigger mode with Aga: GUIDED + RC switch vs ArduPilot PLND (LANDING_TARGET in LAND). Current code sends velocity in LAND → ignored by FC | Written decision (1 paragraph) + FSM updated | Aga: PID/Direct-Landing design, which mode his loop lives in | Fathir + Aga | [16 empty] | Not started
1.1.3 | Pi 5 bring-up: OS, venv, camera driver (OV9281), UART map (FC and gimbal must NOT share /dev/serial0), power from BEC | Pi boots on drone power; camera streams; 2 UARTs assigned | Aga: wiring pinout, BEC spec | Fathir | [16 empty] | Not started
1.1.4 | Real FC link, props OFF: set SERIALx_PROTOCOL=2 / BAUD=921, request msg rates (SET_MESSAGE_INTERVAL), measure real Hz + packet loss | Log: ATTITUDE ≥50 Hz, LOCAL_POS ≥50 Hz, rangefinder ≥20 Hz, loss <1% | Aga: wiring done (Okt W3–W4), FC param access | Fathir | [16 empty] | Not started
1.1.5 | Verify velocity frame (BODY_NED) + setpoint streaming 10–20 Hz + ~3 s FC timeout behaviour in SITL, then on bench (props off, watch commanded vs FC target) | Yaw 90° + vx=+0.5 → moves along nose; timeout behaviour documented | Aga: SITL param file of OUR drone | Fathir | [16 empty] | Not started
1.1.6 | Failsafe design: companion heartbeat loss, Pi crash, camera loss → what FC does (FS_GCS / mode fallback) | Failsafe table + tested in SITL | Aga: FC failsafe params | Fathir + Aga | [16 empty] | Not started
1.1.7 | Gimbal interface: confirm controller type (SimpleBGC serial vs servo PWM via FC) and angle sign/zero | gimbal_iface.py matches real hardware; angle check vs inclinometer | Pasha: ISP controller + servo wiring | Fathir + Pasha | [16 empty] | Not started
1.2 | Kalibrasi kamera (Matriks K) — RE-DO on final hardware | K, dist, extrinsics valid for the mounted camera |  | Fathir
1.2.1 | Print ChArUco board (A3, matte, on rigid board) + nested landing pad (matte, flat); caliper-measure real marker sides | Board + pad ready; OUTER/INNER_MARKER_SIDE_M updated | Aga: pengadaan print/board | Fathir | [16 empty] | Not started
1.2.2 | Intrinsic calibration: lock & glue lens focus, 20–40 ChArUco views at 640×400 detect stream (check 640×400 is binned, not cropped) | RMS < 0.5 px; CAM_K / CAM_DIST in config.py |  | Fathir | [16 empty] | Not started
1.2.3 | Validate K: pad at 0.5 / 1 / 2 / 5 m (tape), centre + corners of image; compare tvec | Distance error < 2% table |  | Fathir | [16 empty] | Not started
1.2.4 | Exposure/gain: fixed short exposure; blur test indoor (booth light) + outdoor | Chosen exposure/gain per venue, documented |  | Fathir | [16 empty] | Not started
1.2.5 | Extrinsics: camera→body axis signs (pad 50 cm fwd / right on stand) + lever-arm offset camera→CG and →landing-gear centre | frames.py rotation verified + translation added | Pasha: ISP CAD / mounted camera position | Fathir | [16 empty] | Not started
1.2.6 | Static noise test: drone on stand at 0.5/1/2/5 m → pose std & reproj-error distribution | EKF_MEAS_POS_STD (vs height) + REPROJ_ERR_MAX_PX set from data |  | Fathir | [16 empty] | Not started
1.2.x | Recalibrate if lens/mount changes after ISP rework (contingency) | Only if mount changed | Pasha | Fathir | [16 empty] | Not started
2 | Mekanik & Hardware ISP (Pasha) — dependencies
2.2 | Fabrikasi / perakitan ISP | → needed before final camera mount |  | Pasha
2.3 | Instalasi Motor Servo & ISP | → blocks 1.2.5 extrinsics + 1.1.7 gimbal |  | Pasha
1.3 | Wiring Alat (Aga) | → blocks 1.1.4 real FC link |  | Aga
3 | Sistem Kendali & Logika (Aga) — dependencies
3.1 | Set up ArduPilot SITL | → I plug the companion into it (4.1.1) |  | Aga
3.2 | Implementasi PID Cascade (GPS & Non-GPS) | → needs my latency number (4.1.3) |  | Aga
3.3 | Logika Direct Landing (< 110 cm) | → needs inner-marker lock above 110 cm (4.1.4) |  | Aga
4 | Pengujian & Validasi
4.1 | Uji Simulasi & Deteksi ArUco | Detection + closed-loop evidence on real hardware for Bab 4 |  | Fathir
4.1.1 | Companion ↔ ArduPilot SITL closed loop through REAL pymavlink path (not MockMavlink), with our drone's params | SITL landing on static pad; residual logged | Aga: SITL running (3.1) | Fathir | [16 empty] | Not started
4.1.2 | Detection-rate vs height on REAL footage (handheld / pole at fixed heights) → feed exp_detection_rate.py; tune DetectorParameters | Detection-rate per AGL band ≥ 95% (or documented limit) |  | Fathir | [16 empty] | Not started
4.1.3 | Latency bench on Pi 5 with real camera (photon→setpoint) | LATENCY_ALLOC_MS measured; number sent to Aga for Kp limit |  | Fathir | [16 empty] | Not started
4.1.4 | Handoff / FOV check with real K: height where outer leaves FOV, inner lock height vs Direct Landing 110 cm; set HANDOFF_AGL_M | Handoff table; inner locked well above 110 cm | Aga: Direct-Landing threshold final | Fathir + Aga | [16 empty] | Not started
4.1.5 | HITL bench: Pi + real FC props OFF, move pad under drone by hand → check setpoint signs/magnitudes | Setpoints point toward pad in all 4 directions | Aga: FC ready | Fathir | [16 empty] | Not started
4.1.6 | Tethered / low hover with pad: perception log only (control still manual/PID) | Flight log: detection rate & noise in real flight | Aga: drone flies stably (3.2) | Fathir + Aga | [16 empty] | Not started
4.1.7 | Field detection test (official slot): detection rate vs AGL in flight, indoor + outdoor | Bab 4 table + plot (detection_rate_vs_agl) | Aga: pilot | Fathir | [16 empty] | Not started
4.1.8 | Closed-loop vision landing: static pad → moving pad | Pose + setpoint logs handed to Pasha for MAE | Aga: PID + Direct Landing ready | Fathir + Aga | [16 empty] | Not started
4.1.9 | Write-up: Bab 4 results for my items, figures, limits | Draft section to team |  | Fathir | [16 empty] | Not started
4.2 | Set-up & Analisis MAE & Radius Pendaratan (Pasha) | ← I supply time-synced pose/setpoint logs + lever-arm |  | Pasha
Progress | Sub-tasks done | 0 / 24
| % done | 0%
| Blocked | 0
Legend
My work week
No-work week (Timelinev2)
Teammate slot I depend on
Meeting / report
Section header
Assumptions
• Week split W1=1–7, W2=8–14, W3=15–21, W4=22–end of month (Timelinev2 has no dates; adjust if your weeks are Mon-based).
• Okt W1 only has 6–7 Oct left, so it holds short tasks only.
• Sep items 1.1 / 1.2 counted as done on the SITL/placeholder level; the 1.x.y rows here are the redo on the physical drone.
• Teammate slots (grey) copied from Timelinev2 as of 6 Oct 2026. If they move, my dependent rows move with them.

## To-Do Mingguan
Weekly checklist — Fathir (tick Status as you go)
Minggu | Tanggal | WBS | To-do | Done when… | Butuh dari | Status | Catatan
Okt W1 | 6–7 Okt | 1.1.0 | Send comms/calibration status section for laporan kemajuan to Aga | Aga has the text + 1–2 figures | Aga: template | Not started
Okt W1 | 6–7 Okt | 1.1.1 | Branch + start MAVLink reader-thread refactor (latest-message cache) | Runs against SITL without missing ATTITUDE |  | Not started
Okt W1 | 6–7 Okt | 1.2.1 | Generate ChArUco board PDF + pad PDF; ask Aga to buy print (matte, rigid) | Order placed | Aga: pengadaan | Not started
Okt W2 | 8–14 Okt | — | NO WORK WEEK (laporan kemajuan due)
Okt W3 | 15–21 Okt | 1.1.1 | Finish reader thread; stale-data handling; unit test with MockMavlink | Tests pass |  | Not started
Okt W3 | 15–21 Okt | 1.1.2 | Meet Aga: GUIDED+switch vs PLND decision; update fsm.py trigger | Decision written in notes.md | Aga | Not started
Okt W3 | 15–21 Okt | 1.1.3 | Pi 5 bring-up on drone: OS, venv, OV9281 stream, UART assignment (FC ≠ gimbal port) | ls -l /dev/serial*; camera frames saved | Aga: pinout | Not started
Okt W3 | 15–21 Okt | 1.2.1 | Measure printed marker sides with calipers → config.py | Sides in config |  | Not started
Okt W3 | 15–21 Okt | 1.2.2 | Lock lens focus; start ChArUco capture | ≥20 views captured |  | Not started
Okt W3 | 15–21 Okt | 0.1 | Client meeting: show live detection on real camera | Demo works |  | Not started
Okt W4 | 22–31 Okt | 1.2.2 | Finish intrinsic calibration at 640×400 (confirm binned, not cropped) | RMS < 0.5 px |  | Not started
Okt W4 | 22–31 Okt | 1.2.3 | Tape-measure validation 0.5/1/2/5 m | Distance error < 2% |  | Not started
Okt W4 | 22–31 Okt | 1.1.4 | Connect Pi↔FC (props off), set SERIAL params, request msg rates, measure Hz + loss | Rates & loss logged | Aga: wiring finished | Not started
Nov W1 | 1–7 Nov | 1.2.4 | Exposure/gain + blur test (indoor + outdoor) | Settings chosen |  | Not started
Nov W1 | 1–7 Nov | 4.1.2 | Record footage at fixed heights (pole/handheld); run detection-rate script on it | Rate per band table |  | Not started
Nov W1 | 1–7 Nov | 1.1.7 | Ask Pasha: gimbal controller type, wiring, angle conventions | gimbal_iface plan | Pasha | Not started
Nov W2 | 8–14 Nov | 4.1.2 | Tune ArUco DetectorParameters on real footage (glare, far range) | ≥95% per band or limit documented |  | Not started
Nov W2 | 8–14 Nov | 4.1.3 | Latency bench on Pi 5 with real camera; send result to Aga | LATENCY_ALLOC_MS measured | → Aga | Not started
Nov W2 | 8–14 Nov | 1.1.7 | Implement/verify gimbal interface on installed ISP | Angles match inclinometer | Pasha: ISP installed | Not started
Nov W2 | 8–14 Nov | 1.1.5 | SITL: verify BODY_NED velocity frame + 3 s timeout | Behaviour documented | Aga: SITL | Not started
Nov W3 | 15–21 Nov | 1.2.5 | Extrinsics: axis-sign test on stand + lever-arm from CAD/ruler → frames.py | Signs correct, offset added | Pasha: CAD | Not started
Nov W3 | 15–21 Nov | 1.2.6 | Static noise test at 4 heights → EKF_MEAS_POS_STD, REPROJ gate | Values from data |  | Not started
Nov W3 | 15–21 Nov | 4.1.1 | Hook companion into Aga's SITL via real pymavlink path | Companion controls SITL drone | Aga: SITL | Not started
Nov W4 | 22–30 Nov | 4.1.1 | SITL closed-loop landing on static pad with our params | Residual logged |  | Not started
Nov W4 | 22–30 Nov | 1.1.6 | Failsafe table (heartbeat/Pi/camera loss) + SITL test | Table + test log | Aga: FS params | Not started
Des W1 | 1–7 Des | 4.1.4 | Handoff/FOV table with real K; set HANDOFF_AGL_M vs 110 cm Direct Landing | Inner lock above 110 cm | Aga: threshold | Not started
Des W1 | 1–7 Des | 4.1.1 | SITL moving-target run; prep plots | Plots for dosen meeting |  | Not started
Des W1 | 1–7 Des | 0.0 | Dosen meeting: SITL closed loop + calibration results |  |  | Not started
Des W2 | 8–14 Des | — | NO WORK WEEK
Des W3 | 15–21 Des | — | NO WORK WEEK
Des W4 | 22–31 Des | 4.1.5 | HITL bench props off: move pad, check setpoint signs/magnitudes | Correct direction all 4 sides | Aga: FC | Not started
Des W4 | 22–31 Des | 1.2.x | Recalibrate only if mount/lens changed |  | Pasha | Not started
Des W4 | 22–31 Des | 0.0/0.1 | Dosen + client meetings |  |  | Not started
Jan W1 | 1–7 Jan | 4.1.6 | Tethered/low hover with pad, perception logging only | Flight log | Aga: stable flight | Not started
Jan W1 | 1–7 Jan | 4.2 | Agree log format/time sync with Pasha for MAE | Pasha can compute MAE from my log | Pasha | Not started
Jan W2 | 8–14 Jan | 4.1.7 | Field detection test in flight (indoor) | Bab 4 table | Aga: pilot | Not started
Jan W2 | 8–14 Jan | 0.1 | Client meeting |  |  | Not started
Jan W3 | 15–21 Jan | 4.1.7 | Field detection test in flight (outdoor) | Plot detection rate vs AGL |  | Not started
Jan W3 | 15–21 Jan | 4.1.8 | Closed-loop landing, static pad | Logs → Pasha | Aga: PID + Direct Landing | Not started
Jan W4 | 22–31 Jan | 4.1.8 | Closed-loop landing, moving pad | Logs → Pasha |  | Not started
Jan W4 | 22–31 Jan | 4.1.9 | Write Bab 4 section for my items | Draft to team |  | Not started
Done | 0 / 38

## Input dari Tim
What I need from the others (ask early, by the 'Needed by' week)
Dari | Apa | Kenapa (dipakai di) | Needed by | Status
Aga | Template + deadline laporan kemajuan | 1.1.0 | Okt W1 | Not asked
Aga | Purchase: ChArUco board print (A3 rigid), matte landing pad print | 1.2.1 | Okt W1 | Not asked
Aga | Wiring pinout: which Pi UART ↔ FC TELEM port, BEC rating for Pi 5 | 1.1.3, 1.1.4 | Okt W3 | Not asked
Aga | Which flight mode his PID / Direct Landing runs in (GUIDED vs LAND+PLND) | 1.1.2 (current code is wrong for real FC) | Okt W3 | Not asked
Aga | Rangefinder model + RNGFND params (AGL source); GPS vs non-GPS EKF source setup | 1.1.4, read_agl / read_velocity_body | Okt W4 | Not asked
Aga | FC parameter file of the real drone (.param) for SITL | 1.1.5, 4.1.1 | Nov W2 | Not asked
Aga | FC failsafe params (FS_GCS etc.) | 1.1.6 | Nov W4 | Not asked
Aga | Final Direct-Landing threshold (110 cm?) and what it expects from vision below it | 4.1.4 handoff | Des W1 | Not asked
Aga | Pilot availability + stable manual/PID flight | 4.1.6–4.1.8 | Jan W1 | Not asked
Pasha | Gimbal controller type (SimpleBGC serial vs servo PWM), wiring, axis sign conventions | 1.1.7 gimbal_iface.py | Nov W1 | Not asked
Pasha | ISP CAD: camera optical centre position vs FC/CG and landing-gear centre | 1.2.5 lever arm | Nov W3 | Not asked
Pasha | Notice if lens/mount changes after calibration | 1.2.x recalibration | Any time | Not asked
Pasha | MAE setup: how ground truth is measured, log format/time sync he needs | 4.1.8 → 4.2 | Jan W1 | Not asked
Me → Aga | Measured latency (photon→setpoint) for his Kp limit | 3.2 | Nov W2 | Not asked
Me → Aga | Height where inner marker is reliably locked | 3.3 | Des W1 | Not asked
Me → Pasha | Lever-arm-corrected pose + setpoint logs | 4.2 MAE | Jan W3 | Not asked

## Parameter Retune
Parameters to (re)determine on the physical drone
Parameter | File | Nilai sekarang | Cara menentukan | Kriteria | WBS | Nilai baru
CAM_K, CAM_DIST | config.py | fx=fy=560, cx=320, cy=200; dist=0 (placeholder) | ChArUco calibration on 640×400 stream, focus locked | RMS < 0.5 px; tape test < 2% | 1.2.2–1.2.3
OUTER/INNER_MARKER_SIDE_M | config.py | 1.250 / 0.100 | Caliper on printed black border; consider smaller outer for real altitude range | ±1 mm | 1.2.1
_NADIR_CAM_TO_BODY | frames.py | diag(1,-1,1) (from synthetic cam) | Pad 50 cm fwd / right of drone on stand, check pos_body signs | Signs correct | 1.2.5
Lever arm (new) | frames.py | none (rotation only) | CAD / ruler: camera centre → CG and → gear centre | ±5 mm | 1.2.5
Gimbal angle sign/zero | gimbal_iface.py | assumed | Tilt by hand vs inclinometer | ±2° | 1.1.7
Exposure / gain | camera setup | auto | Hover/handheld blur test, indoor + outdoor | No visible blur at max speed | 1.2.4
EKF_MEAS_POS_STD | config.py | 0.04 m | Static pose std at 0.5/1/2/5 m (expect ~z²) | From data | 1.2.6
REPROJ_ERR_MAX_PX | config.py | 3.0 px | 1.5 × 99th percentile of good real detections | From data | 1.2.6
DetectorParameters | markers.py | OpenCV defaults + subpix | Tune on real footage (adaptive threshold window, min perimeter) | ≥95% per AGL band | 4.1.2
LATENCY_ALLOC_MS | config.py | sum 40 ms (estimate) | latency_bench.py on Pi 5 + real camera | ≤ 66 ms ceiling | 4.1.3
HANDOFF_AGL_M | config.py | 0.90 m | Real-K FOV calc + test; outer leaves FOV ≈ side·fy / (0.8·400) | Inner locked above Direct-Landing threshold | 4.1.4
FLARE_AGL_M | config.py | 0.28 m | Camera height when landed + lens min focus distance | Measured | 4.1.4
MAVLINK_CONN / BAUD | config.py | udp SITL / 921600 | Real UART device; packet-loss test | Loss < 1% | 1.1.4
GIMBAL_SERIAL_PORT | config.py | /dev/serial0 (clashes w/ FC) | Assign separate UART / USB | No shared port | 1.1.3
Message rates | mavlink_iface.py | not requested | SET_MESSAGE_INTERVAL + measure | ATT/POS ≥50 Hz, AGL ≥20 Hz | 1.1.4
Landing trigger mode | fsm.py / mavlink_iface.py | LAND (custom_mode 9) | Decide with Aga; SITL test | FC actually follows setpoints | 1.1.2
Yellow = fill in the measured value. Current values are read from landing_sw/ on 6 Oct 2026.